## Sheet1
Week | Mo | Tu | We | Th | Fr | Sa | Su | Deliverable | Date
46 |  | "System proposal" pitches and decision |  | "Game proposal" pitches and decision | Finish sketch of game play |  |  | Game sypnosis, {team, action, test} plans | 2014-11-14
|  |  |  | Meeting with company: adopt ideas | Decide on and set-up of software
First sketch of game play
47 |  | Set goals and planning for this week (Design & Software) |  | Finish documentation + send | Evaluate week |  |  | Game design document | 2014-11-21
Game design last changes and documentation
Software and GitHub running
48 |  | Set goals and planning for the week (Design & Software) |  |  | Evaluate week
49 |  | Set goals and planning for the week (Design & Software) |  | Finish prototype | Evaluate week |  |  | Game prototype | 2014-12-05
50 |  | Set goals and planning for the week (Design & Software) |  | Presentation | Evaluate week |  |  | Mid-term presentation | 2014-12-11
51 |  | Set goals and planning for the week (Design & Software) |  |  | Evaluate week |  |  | Game prototype beta | 2014-12-19
52 | Holidays
1 | Holidays
2 |  | Set goals and planning for the week (Design & Software) |  |  | Evaluate week
3 |  | Finish documentation |  | Last improvements |  |  |  | Game prototype & documentation | 2015-01-16
Final presentation
4 | [7 empty] | Final presentation | 2015-01-20
Overall todo list
Week | Start date | Own Milestone |  | Action holder | GitHub Branch | Deadline
46 | 2014-11-10 | Proposal synopsis |  | Arnold |  | 2014-11-13
|  | Hand in game synopsis to Prof |  | Ralf |  | 2014-11-14
|  | Set up GitHub |  | Ralf |  | 2014-11-14
47 | 2014-11-17 | Game play design |  | David |  | 2014-11-17
|  | Set up software |  | Ismini |  | 2014-11-17
|  | Hand in game design document |  | Ralf |  | 2014-11-21
48 | 2014-11-24
49 | 2014-12-01 | Hand in game prototype |  | Ralf |  | 2014-12-05
50 | 2014-12-08 | Finish and prepare presentation (2 persons!) |  | Ralf (you can delegate) |  | 2014-12-09
51 | 2014-12-15 | Hand in game prototype Beta |  | Ralf |  | 2014-12-19
|  | Invite company for final presentation |  | Ralf |  | 2014-12-19
52 | 2014-12-22
1 | 2014-12-29
2 | 2015-01-05
3 | 2015-01-12 | Hand in game prototype & documentation |  | Ralf |  | 2015-01-16
4 | 2015-01-19 | Finish and prepare presentation (2 persons!) |  | Ralf (you can delegate) |  | 2015-01-19